## Slide 1: Software Project Management
Dr. Tulika

## Slide 2: Outline
Introduction to Project Planning
Software Cost Estimation
  Cost Estimation Models
  Software Size Metrics
  Empirical Estimation
  Heuristic Estimation
  COCOMO
Staffing Level Estimation

## Slide 3: Introduction
Many software projects fail:
  due to faulty project management practices:
    It is important to learn different aspects of software project management.

## Slide 4: Introduction
Goal of software project management:
  enable a group of engineers to work efficiently towards successful completion of a software project.

## Slide 5: Responsibility of project managers
Project proposal writing,
Project cost estimation,
Scheduling,
Project staffing,
Project monitoring and control,
Software configuration management,
Risk management,
Managerial report writing and presentations, etc.

## Slide 6: Introduction
A project manager’s activities are varied.
  can be broadly classified into:
    project planning,
    project monitoring and control activities.

## Slide 7: Project Planning
Once a project is found to be feasible,
  project managers undertake project planning.

## Slide 8: Project Planning Activities
Estimation:
  Effort, cost, resource, and project duration
Project scheduling:
Staff organization:
  staffing plans
Risk handling:
  identification, analysis, and abatement procedures
Miscellaneous plans:
  quality assurance plan, configuration management plan, etc.

## Slide 9: Project planning
Requires utmost care and attention --- commitments to unrealistic time and resource estimates result in:
  irritating delays.
  customer dissatisfaction
  adverse affect on team morale
    poor quality work
  project failure.

## Slide 10: SPMP Document
After planning is complete:
  Document the plans:
  in a Software Project Management Plan(SPMP) document.

## Slide 11: Organization of SPMP Document
  Introduction (Objectives, Major Functions, Performance Issues, Management and Technical Constraints)
  Project Estimates (Historical Data, Estimation Techniques, Effort, Cost, and Project Duration Estimates)
  Project Resources Plan (People, Hardware and Software, Special Resources)
  Schedules (Work Breakdown Structure, Task Network, Gantt Chart Representation, PERT Chart Representation)
  Risk Management Plan (Risk Analysis, Risk Identification, Risk Estimation, Abatement Procedures)
  Project Tracking and Control Plan
  Miscellaneous Plans(Process Tailoring, Quality Assurance)

## Slide 12: Software Cost Estimation
Determine size of the product.
From the size estimate,
  determine the effort needed.
From the effort estimate,
  determine project duration, and cost.

## Slide 13
Size Estimation
Effort Estimation
Cost Estimation
Duration Estimation
Staffing Estimation
Scheduling
Software Cost Estimation

## Slide 14: Software Cost Estimation
Three main approaches to estimation:
  Empirical
  Heuristic
  Analytical

## Slide 15: Software Cost Estimation Techniques
Empirical techniques:
  an educated guess based on past experience.
Analytical techniques:
  derive the required results starting from certain simple assumptions.
Heuristic techniques:
  assume that the characteristics to be estimated can be expressed in terms of some mathematical expression.

## Slide 16: Software Size Metrics
LOC (Lines of Code):
  Simplest and most widely used metric.
  Comments and blank lines should not be counted.

## Slide 17: Disadvantages of Using LOC
Size can vary with coding style.
Focuses on coding activity alone.
Correlates poorly with quality and efficiency of code.
Penalizes higher level programming languages, code reuse, etc.

## Slide 18: Disadvantages of Using LOC (cont...)
Measures textual complexity only.
  does not address the issues of structural or logical complexity.
Difficult to estimate LOC from problem description.
  So not useful for project planning

## Slide 19: Function Point Metric
Overcomes some of the shortcomings of the LOC metric
It is actually computed in 3 steps
  Compute the unadjusted function point(UFP)
  UFP=4* No. of inputs + 5 * No. of Outputs + 4 * No. of inquiries + 10 * No. of files + 10 * No. of interfaces
  UFP is refined to reflect the differences in the complexities of different parameters
  FP is calculated using
    FP=UFP * TCF
      Where TCF is Technical Complexity Factor (vary from 0.65 to 1.35)

## Slide 20: Function Point Metric
Output:
  A set of related outputs is counted as one output.
Inquiries:
  Each user query type is counted.
Files:
  Files are logically related data and thus can be data structures or physical files.
Interface:
  Data transfer to other systems.

## Slide 21: Refinement of FP entities
Type | Simple | Average | Complex
Input | 3 | 4 | 6
Output | 4 | 5 | 7
Inquiry | 3 | 4 | 6
No. of files | 7 | 10 | 15
No. of Interfaces | 5 | 7 | 10

## Slide 22: Function Point Metric (CONT.)
Suffers from a major drawback:
  the size of a function is considered to be independent of its complexity.
Extend function point metric:
  Feature Point metric:
  considers an extra parameter:
    Algorithm Complexity.

## Slide 23: Function Point Metric (CONT.)
Proponents claim:
  FP is language independent.
  Size can be easily derived from problem description
Opponents claim:
  it is subjective --- Different people can come up with different estimates for the same problem.

## Slide 24: Empirical Size Estimation Techniques
Expert Judgement:
  An euphemism for guess made by an expert.
  Suffers from individual bias.
Delphi Estimation:
  overcomes some of the problems of expert judgement.

## Slide 25: Expert judgement
Experts divide a software product into component units:
  e.g. GUI, database module, data communication module, billing module, etc.
Add up the guesses for each of the components.

## Slide 26: Delphi Estimation:
Team of Experts and a coordinator.
Experts carry out estimation independently:
  mention the rationale behind their estimation.
  coordinator notes down any extraordinary rationale:
    circulates among experts.

## Slide 27: Delphi Estimation:
Experts re-estimate.
Experts never meet each other
  to discuss their viewpoints.

## Slide 28: Halstead's Software Science
An analytical technique to estimate:
  size,
  development effort,
  development time.

## Slide 29: Halstead's Software Science
Halstead used a few primitive program parameters
  number of operators and operands
Derived expressions for:
  over all program length,
  potential minimum volume
  actual volume,
  language level,
  effort, and
  development time.

## Slide 30: Halstead's Software Science
First we need to compute the following numbers, given the program:
  n1 = the number of distinct operators
  n2 = the number of distinct operands
  N1 = the total number of operators
  N2 = the total number of operands

## Slide 31: Halstead’s Software Science
Program length (N)
  The program length (N) is the sum of the total number of operators and operands in the program:
  N = N1 + N2
Vocabulary size (n)
  The vocabulary size (n) is the sum of the number of unique operators and operands:
  n = n1 + n2
Program volume (V)
The program volume (V) is the information contents of the program, measured in mathematical bits.
V = N * log2(n)
  Halstead's volume (V) describes the size of the implementation of an algorithm. The computation of V is based on the number of operations performed and operands handled in the algorithm. Therefore V is less sensitive to code layout than the lines-of-code measures.
  The volume of a function should be at least 20 and at most 1000. The volume of a parameter less one-line function that is not empty; is about 20. A volume greater than 1000 tells that the function probably does too many things.
  The volume of a file should be at least 100 and at most 8000.

## Slide 32: Halstead’s Software Science
Difficulty level (D)
The difficulty level or error proneness (D) of the program is proportional to the number of unique operators in the program. D is also proportional to the ratio between the total number of operands and the number of unique operands (i.e. if the same operands are used many times in the program, it is more prone to errors).
D = ( n1 / 2 ) * ( N2 / n2 )
Program level (L)
  The program level (L) is the inverse of the error proneness of the program i.e. a low level program is more prone to errors than a high level program.
L = 1 / D

## Slide 33: Halstead’s Software Science
Effort to implement (E)
  The effort to implement (E) or understand a program is proportional to the volume and to the difficulty level of the program.
E = V * D
Estimated Program Length N= n1log2n1+n2log2n2
Potential Volume: V*= (2+n2*) log2( 2+n2*)
Estimated program Level/difficulty
  L =2n2/n1N2
  Hence, D =1 /L

## Slide 34: Halstead’s Software Science
Effort:
  Halstead hypothesized that the effort required to implement a program increases as the size of the program increases. It takes more effort to implement a program at a lower level than the higher level.
E= V/L
Time to implement (T)
  John Stroud suggested that human mind is capable of making a limited number of elementary discriminations per second. Stroud claims that β (Stroud number) ranges between 5 to 20.
  T = E / β
    β is normally set to 18 since this seemed to give best results in Halstead earliest experiments

## Slide 35: Example
Consider following C program
  main()
  {
  int a, b, c, avg;
  scanf (“%d%d%d”, &a, &b,&c);
  avg = (a + b + c) / 3;
  printf (“avg=%d”, avg);
  }

## Slide 36: COCOMO Model
COCOMO (COnstructive COst MOdel) proposed by Boehm.
Divides software product developments into 3 categories:
  Organic
  Semidetached
  Embedded

## Slide 37: COCOMO Product classes
Roughly correspond to:
  application, utility and system programs respectively.
    Data processing and scientific programs are considered to be application programs.
    Compilers, linkers, editors, etc., are utility programs.
    Operating systems and real-time system programs, etc. are system programs.

## Slide 38: Elaboration of Product classes
Organic:
  Relatively small groups
    working to develop well-understood applications.
Semidetached:
  Project team consists of a mixture of experienced and inexperienced staff.
Embedded:
  The software is strongly coupled to complex hardware, or real-time systems.

## Slide 39: COCOMO Model (CONT.)
For each of the three product categories:
  From size estimation (in KLOC), Boehm provides equations to predict:
    project duration in months
    effort in programmer-months
Boehm obtained these equations:
  examined historical data collected from a large number of actual projects.

## Slide 40: COCOMO Model (CONT.)
Software cost estimation is done through three stages:
  Basic COCOMO,
  Intermediate COCOMO,
  Complete COCOMO.

## Slide 41: Basic COCOMO Model (CONT.)
Gives only an approximate estimation:
  Effort = a1 * (KLOC)a2
  Tdev = b1 * (Effort)b2
    KLOC is the estimated kilo lines of source code,
    a1,a2,b1,b2 are constants for different categories of software products,
    Tdev is the estimated time to develop the software in months,
    Effort estimation is obtained in terms of person months (PMs).

## Slide 42: Development Effort Estimation
Organic :
  Effort = 2.4 * (KLOC)1.05 PM
Semi-detached:
  Effort = 3.0 * (KLOC)1.12 PM
Embedded:
  Effort = 3.6 * (KLOC)1.20 PM

## Slide 43: Development Time Estimation
Organic:
  Tdev = 2.5 * (Effort)0.38 Months
Semi-detached:
  Tdev = 2.5 * (Effort)0.35 Months
Embedded:
  Tdev = 2.5 * (Effort)0.32 Months

## Slide 44: Basic COCOMO Model (CONT.)
Effort is somewhat super-linear in problem size.
Effort
Size
Embedded
Semidetached
Organic

## Slide 45: Basic COCOMO Model (CONT.)
Development time
  sublinear function of product size.
When product size increases two times,
  development time does not double.
Time taken:
  almost same for all the three product categories.
Size
Dev. Time
Embedded
Semidetached
Organic
60K
18 Months
14 Months
30K

## Slide 46: Basic COCOMO Model (CONT.)
Development time does not increase linearly with product size:
  For larger products more parallel activities can be identified:
    can be carried out simultaneously by a number of engineers.

## Slide 47: Example
Assume that the size of an organic software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software developers is Rs. 15000 per month. Determine the effort required to develop the software product, the nominal development time and cost to develop the product.

## Slide 48: Example
  Effort = 2.4*(32)1.05 = 91 PM
  Nominal development time = 2.5*(91)0.38 = 14 months
  Cost = effort * salary per month = 91 * 15000 = 1365000

## Slide 49: Intermediate COCOMO
Basic COCOMO model assumes
  effort and development time depend on product size alone.
However, several parameters affect effort and development time:
    Reliability requirements
    Availability of CASE tools and modern facilities to the developers
    Size of data to be handled

## Slide 50: Intermediate COCOMO
For accurate estimation,
  the effect of all relevant parameters must be considered:
  Intermediate COCOMO model recognizes this fact:
    refines the initial estimate obtained by the basic COCOMO by using a set of 15 cost drivers (multipliers).

## Slide 51: Intermediate COCOMO (CONT.)
If modern programming practices are used,
  initial estimates are scaled downwards.
If there are stringent reliability requirements on the product :
  initial estimate is scaled upwards.

## Slide 52: Intermediate COCOMO (CONT.)
Rate different parameters on a scale of one to three:
  Depending on these ratings,
    multiply cost driver values with the estimate obtained using the basic COCOMO.

## Slide 53: Intermediate COCOMO (CONT.)
Cost driver classes:
  Product: Inherent complexity of the product, reliability requirements of the product, etc.
  Computer: Execution time, storage requirements, etc.
  Personnel: Experience of personnel, etc.
  Development Environment: Sophistication of the tools used for software development.

## Slide 54: COCOMO 2
COCOMO II is actually a hierarchy of estimation models that address the following areas:
  Application composition model. Used during the early stages of software engineering, when prototyping of user interfaces, consideration of software and system interaction, assessment of performance, and evaluation of technology maturity are paramount.
  Early design stage model. Used once requirements have been stabilized and basic software architecture has been established.
  Post-architecture-stage model. Used during the construction of the software.

## Slide 55: Application Composition Model
Based on counting the number of screens, reports and 3GL components
Each of these components are objects.

## Slide 56: Effort estimation steps
  Estimate the number of screens, reports, and 3GL components from analysis of SRS document
  Determine complexity level of each screen and report and rate these as simple, medium or difficult.
  Screen complexity
  Report complexity
No. of views | Table<4 | Table<8 | Table>=8
<3 | Simple | Simple | Medium
3-7 | Simple | Medium | Difficult
>8 | medium | Difficult | Difficult
No. of sections | Table<4 | Table<8 | Table>=8
0 or 1 | Simple | Simple | Medium
2 or 3 | Simple | Medium | Difficult
4 or more | medium | Difficult | Difficult

## Slide 57: Effort estimation steps
Use the weight values
Determine the number of objects points( Add all the assigned complexity values for the object instances together)
Estimate percentage reuse expected in the system. Then evaluate New Object Point (NOP)
  NOP= (Object Points)(100 - % of reuse)/100
Determine Productivity rate using the following table
  PROD= NOP/Person Month
Finally, the person month is computed as E= NOP/PROD
Object Type | Simple | Medium | Difficult
Screen | 1 | 2 | 3
Reports | 2 | 5 | 8
3GL components | - | - | 10
Developer’s exp | Very low | Low | Nominal | High | Very high
CASE maturity | Very low | Low | Nominal | High | Very high
PROD | 4 | 7 | 13 | 25 | 50

## Slide 58: Early Design Model
Effort = KLOC * ∏i costdriver i
Cost driver classes:
  Product: Inherent complexity of the product, reliability requirements of the product, etc.
  Computer: Execution time, storage requirements, etc.
  Personnel: Experience of personnel, etc.
  Development Environment: Sophistication of the tools used for software development.

## Slide 59: Post Architectural Model
Effort = a * KLOCb * ∏i costdriver i
  where a=2.5 and b is between 1.01 to 1.26

## Slide 60: Staffing Level Estimation
Number of personnel required during any development project:
  not constant.
Norden in 1958 analyzed many R&D projects, and observed:
  Rayleigh curve represents the number of full-time personnel required at any time.

## Slide 61: Rayleigh Curve
Rayleigh curve is specified by two parameters:
  td the time at which the curve reaches its maximum
  K the total area under the curve.
L=f(K, td)
Effort
Time
td
Rayleigh Curve

## Slide 62: Putnam’s Work:
In 1976, Putnam studied the problem of staffing of software projects:
  observed that the level of effort required in software development efforts has a similar envelope.
  found that the Rayleigh-Norden curve
    relates the number of delivered lines of code to effort and development time.

## Slide 63: Putnam’s Work (CONT.):
Putnam analyzed a large number of army projects, and derived the expression: L=Ck*K1/3 * td4/3
  K is the effort expended and L is the size in KLOC.
  td is the time to develop the software.
  Ck is the state of technology constant
    reflects factors that affect programmer productivity.

## Slide 64: Putnam’s Work (CONT.):
Ck=2 for poor development environment
  no methodology, poor documentation, and review, etc.
Ck=8 for good software development environment
  software engineering principles used
Ck=11 for an excellent environment

## Slide 65: Rayleigh Curve
Very small number of engineers are needed at the beginning of a project
  carry out planning and specification.
As the project progresses:
  more detailed work is required,
  number of engineers slowly increases and reaches a peak.

## Slide 66: Rayleigh Curve
Putnam observed that:
  the time at which the Rayleigh curve reaches its maximum value
    corresponds to system testing and product release.
  After system testing,
    the number of project staff falls till product installation and delivery.

## Slide 67: Rayleigh Curve
From the Rayleigh curve observe that:
  approximately 40% of the area under the Rayleigh curve is to the left of td
  and 60% to the right.

## Slide 68: Effect of Schedule Change on Cost
Using the Putnam's expression for L, K=L3/Ck3td4 Or, K=C1/td4
  For the same product size, C1=L3/Ck3 is a constant.
Or, K1/K2 = td24/td14

## Slide 69: Effect of Schedule Change on Cost (CONT.)
Observe:
  a relatively small compression in delivery schedule
    can result in substantial penalty on human effort.
Also, observe:
  benefits can be gained by using fewer people over a somewhat longer time span.

## Slide 70: Example
If the estimated development time is 1 year, then in order to develop the product in 6 months,
  the total effort and hence the cost increases 16 times.
  In other words,
    the relationship between effort and the chronological delivery time is highly nonlinear.